## Task Plan
HOPE, Inc. ERP - Planned Tasks per Team Member per Sprint
Each task is one planned PR. Enter the member's name, update Status as work progresses (Merged = done), and paste the PR link. Use the filter on row 4 to view one sprint or one role. Light-blue cells were revised to add User Management and Reports (see Change Log).
Task ID | Sprint | Week | Role | Assigned to (name) | Task (one PR) | Due (sprint day) | Status | PR link | Notes
S1-DEV-01 | 1 | 1 | Developer |  | Project scaffold: app skeleton, env config, DB connection | 2 | Not started
S1-DEV-02 | 1 | 1 | Developer |  | Register user form and API (new users start as pending) | 4 | Not started
S1-DEV-03 | 1 | 2 | Developer |  | Login and logout with session handling; password hashing and set-password on first login; blocked users cannot sign in | 6 | Not started
S1-DEV-04 | 1 | 2 | Developer |  | Reset password: request, emailed token, reset form | 7 | Not started
S1-DEV-05 | 1 | 2 | Developer |  | User Management screen: user list, Add User, Edit User, Block/Unblock; Admin manages Users only and Superadmin accounts are hidden | 8 | Not started
S1-DEV-06 | 1 | 2 | Developer |  | Superadmin: approve pending users and designate admins; block removing or disabling the last remaining superadmin | 8 | Not started
S1-DEV-07 | 1 | 2 | Developer |  | Rights dialog: admin/superadmin assign per-action rights by module (Customer, Product, Human Resources, Sales, Reports) with module checkbox and All/None; log every rights change in audit_log | 9 | Not started
S1-DEV-08 | 1 | 2 | Developer |  | Main page: sidebar and module tiles by role and rights, plus server-side permission check | 9 | Not started
S1-DBA-01 | 1 | 1 | DB Admin |  | Team database setup, migration runner script, and student setup README (no Docker) | 2 | Not started
S1-DBA-02 | 1 | 1 | DB Admin |  | Migration: HOPE base tables and sample data from HopeDB_audit.sql | 3 | Not started
S1-DBA-03 | 1 | 1 | DB Admin |  | Migration: app_user (role, blocked flag), role, module, rights catalogue, user_permission (with soft delete) | 4 | Not started
S1-DBA-04 | 1 | 1 | DB Admin |  | Migration: password reset token table (hashed, expiry, used flag) | 5 | Not started
S1-DBA-05 | 1 | 1 | DB Admin |  | Seed data: one superadmin account per team member, modules (Customer, Product, Human Resources, Sales, Reports), the per-action rights catalogue (36 rights, guide 3.8), default roles (no passwords in the repo; first password set via one-time set-password link) | 5 | Not started
S1-DBA-06 | 1 | 2 | DB Admin |  | Make audit_user() record the logged-in user in audit_log; test it | 8 | Not started
S1-TST-01 | 1 | 1 | Tester |  | Sprint 1 test plan and acceptance criteria | 3 | Not started
S1-TST-02 | 1 | 2 | Tester |  | Test cases: register, login and logout, set and reset password (expired and reused token) | 7 | Not started
S1-TST-03 | 1 | 2 | Tester |  | Test cases: User Management (add, edit, block/unblock, approve, designate admin; Admin cannot see or edit Superadmin; last-superadmin guard) | 8 | Not started
S1-TST-04 | 1 | 2 | Tester |  | Permission matrix tests (superadmin/admin/user x each right), using registered and approved test accounts; menu, buttons and server all follow the rights | 9 | Not started
S1-TST-05 | 1 | 2 | Tester |  | Automated smoke test: login and main page | 9 | Not started
S1-TST-06 | 1 | 2 | Tester |  | Bug reports and fix verification | 9 | Not started
S1-UIX-01 | 1 | 1 | UI/UX Designer |  | Design system: colors, typography, core components | 2 | Not started
S1-UIX-02 | 1 | 1 | UI/UX Designer |  | Wireframes: login, register, set/reset password | 3 | Not started
S1-UIX-03 | 1 | 1 | UI/UX Designer |  | Wireframes: main page, User Management list and Rights dialog | 4 | Not started
S1-UIX-04 | 1 | 2 | UI/UX Designer |  | Hi-fi mockups (login, register, main page, User Management, Rights dialog) and developer handoff notes | 6 | Not started
S1-UIX-05 | 1 | 2 | UI/UX Designer |  | Usability review of built screens and fix list | 9 | Not started
S1-SM-01 | 1 | 1 | Scrum Master |  | Repo setup: branch protection, PR and issue templates | 1 | Not started
S1-SM-02 | 1 | 1 | Scrum Master |  | Sprint 1 board: stories with acceptance criteria; map all six guide modules to sprints within the 8-week limit | 1 | Not started
S1-SM-03 | 1 | 1 | Scrum Master |  | Team working agreement, Definition of Done, role guide | 2 | Not started
S1-SM-04 | 1 | 1 | Scrum Master |  | Mid-sprint check notes and impediment log | 5 | Not started
S1-SM-05 | 1 | 2 | Scrum Master |  | Sprint 1 review and retrospective report | 10 | Not started
S2-DEV-01 | 2 | 3 | Developer |  | Customer list with search and filter (permission-checked) | 2 | Not started
S2-DEV-02 | 2 | 3 | Developer |  | Customer create and edit form | 3 | Not started
S2-DEV-03 | 2 | 3 | Developer |  | Customer soft delete and restore | 4 | Not started
S2-DEV-04 | 2 | 3 | Developer |  | Product list with search and filter | 5 | Not started
S2-DEV-05 | 2 | 4 | Developer |  | Product create and edit form | 6 | Not started
S2-DEV-06 | 2 | 4 | Developer |  | Product soft delete and restore | 7 | Not started
S2-DEV-07 | 2 | 4 | Developer |  | Price history: add, edit and delete price with effective date | 8 | Not started
S2-DEV-08 | 2 | 4 | Developer |  | Current-price display on product page; per-action rights checks (Add/Edit/Delete) across both modules | 9 | Not started
S2-DBA-01 | 2 | 3 | DB Admin |  | Customer and product active views, indexes | 2 | Not started
S2-DBA-02 | 2 | 3 | DB Admin |  | Query: current price as of a given date | 4 | Not started
S2-DBA-03 | 2 | 3 | DB Admin |  | Validation constraints (payTerms, unit) | 5 | Not started
S2-DBA-04 | 2 | 4 | DB Admin |  | Verify child-record delete checks for customer and product | 6 | Not started
S2-DBA-05 | 2 | 4 | DB Admin |  | Demo data for customer, product, price history | 7 | Not started
S2-DBA-06 | 2 | 4 | DB Admin |  | Search performance check and index tuning | 9 | Not started
S2-TST-01 | 2 | 3 | Tester |  | Test cases: customer module | 3 | Not started
S2-TST-02 | 2 | 3 | Tester |  | Test cases: product and price history | 5 | Not started
S2-TST-03 | 2 | 4 | Tester |  | Soft delete/restore tests, incl. delete blocked by active children | 7 | Not started
S2-TST-04 | 2 | 4 | Tester |  | Per-right permission tests for customer and product (Add/Edit/Delete, price rights) | 8 | Not started
S2-TST-05 | 2 | 4 | Tester |  | Regression test of Sprint 1 | 9 | Not started
S2-TST-06 | 2 | 4 | Tester |  | Bug reports and fix verification | 9 | Not started
S2-UIX-01 | 2 | 3 | UI/UX Designer |  | Wireframes: customer screens | 2 | Not started
S2-UIX-02 | 2 | 3 | UI/UX Designer |  | Wireframes: product and price history screens | 3 | Not started
S2-UIX-03 | 2 | 3 | UI/UX Designer |  | Hi-fi mockups and handoff notes | 5 | Not started
S2-UIX-04 | 2 | 4 | UI/UX Designer |  | Empty, error and confirm-delete states | 7 | Not started
S2-UIX-05 | 2 | 4 | UI/UX Designer |  | Usability review of built screens | 9 | Not started
S2-SM-01 | 2 | 3 | Scrum Master |  | Sprint 2 planning notes and board | 1 | Not started
S2-SM-02 | 2 | 3 | Scrum Master |  | Follow up Sprint 1 retro actions | 3 | Not started
S2-SM-03 | 2 | 3 | Scrum Master |  | Mid-sprint check and impediment log | 5 | Not started
S2-SM-04 | 2 | 4 | Scrum Master |  | Update velocity and burndown | 8 | Not started
S2-SM-05 | 2 | 4 | Scrum Master |  | Sprint 2 review and retrospective report | 10 | Not started
S3-DEV-01 | 3 | 5 | Developer |  | Department list and CRUD | 2 | Not started
S3-DEV-02 | 3 | 5 | Developer |  | Job list and CRUD | 3 | Not started
S3-DEV-03 | 3 | 5 | Developer |  | Employee list with search and filter | 4 | Not started
S3-DEV-04 | 3 | 5 | Developer |  | Employee create and edit form | 5 | Not started
S3-DEV-05 | 3 | 6 | Developer |  | Employee soft delete/restore and separation date | 6 | Not started
S3-DEV-06 | 3 | 6 | Developer |  | Job history: add, edit and delete promotion or transfer (effective date, salary) | 7 | Not started
S3-DEV-07 | 3 | 6 | Developer |  | Employee profile with job timeline | 8 | Not started
S3-DEV-08 | 3 | 6 | Developer |  | Restrict job history and salary visibility with the View Job History right | 9 | Not started
S3-DBA-01 | 3 | 5 | DB Admin |  | Views/queries: employee current job and department | 2 | Not started
S3-DBA-02 | 3 | 5 | DB Admin |  | Job history validation (no duplicate effective dates) | 4 | Not started
S3-DBA-03 | 3 | 5 | DB Admin |  | Link app_user.empno to employee | 5 | Not started
S3-DBA-04 | 3 | 6 | DB Admin |  | Verify child-record delete checks for employee, department, job | 6 | Not started
S3-DBA-05 | 3 | 6 | DB Admin |  | HR demo data | 7 | Not started
S3-DBA-06 | 3 | 6 | DB Admin |  | Indexes and backup/restore script | 9 | Not started
S3-TST-01 | 3 | 5 | Tester |  | Test cases: department and job | 3 | Not started
S3-TST-02 | 3 | 5 | Tester |  | Test cases: employee | 5 | Not started
S3-TST-03 | 3 | 6 | Tester |  | Job history tests (effective date, salary) | 7 | Not started
S3-TST-04 | 3 | 6 | Tester |  | Salary visibility and HR per-right permission tests | 8 | Not started
S3-TST-05 | 3 | 6 | Tester |  | Regression test of Sprints 1-2 | 9 | Not started
S3-TST-06 | 3 | 6 | Tester |  | Bug reports and fix verification | 9 | Not started
S3-UIX-01 | 3 | 5 | UI/UX Designer |  | Wireframes: department and job screens | 2 | Not started
S3-UIX-02 | 3 | 5 | UI/UX Designer |  | Wireframes: employee and profile screens | 3 | Not started
S3-UIX-03 | 3 | 5 | UI/UX Designer |  | Job timeline component design | 4 | Not started
S3-UIX-04 | 3 | 5 | UI/UX Designer |  | Hi-fi mockups and handoff notes | 5 | Not started
S3-UIX-05 | 3 | 6 | UI/UX Designer |  | Usability review of built screens | 9 | Not started
S3-SM-01 | 3 | 5 | Scrum Master |  | Sprint 3 planning notes and board | 1 | Not started
S3-SM-02 | 3 | 5 | Scrum Master |  | Re-prioritize any Sprint 2 carryover | 3 | Not started
S3-SM-03 | 3 | 5 | Scrum Master |  | Mid-sprint check and impediment log | 5 | Not started
S3-SM-04 | 3 | 6 | Scrum Master |  | Update velocity and Sprint 4 risk register | 8 | Not started
S3-SM-05 | 3 | 6 | Scrum Master |  | Sprint 3 review and retrospective report | 10 | Not started
S4-DEV-01 | 4 | 7 | Developer |  | Sales list with search and New Sale header (auto-numbered transaction, customer and salesperson drop-downs) | 3 | Not started
S4-DEV-02 | 4 | 7 | Developer |  | Sale details: add, edit and delete line items (product, quantity); auto-fill unit price from price history as of sales date | 5 | Not started
S4-DEV-03 | 4 | 8 | Developer |  | Record payment against a transaction | 6 | Not started
S4-DEV-04 | 4 | 8 | Developer |  | Reports module, part 1: Product Master List, Active Employees, All Employees, Employee Job History (per-report rights, Print / Save as PDF) | 6 | Not started
S4-DEV-05 | 4 | 8 | Developer |  | Reports module, part 2: Top Customers, Top Products, Top Sales (date range, Top N, per-report rights, Print / Save as PDF) | 7 | Not started
S4-DEV-06 | 4 | 8 | Developer |  | Balance view per transaction and customer | 7 | Not started
S4-DEV-07 | 4 | 8 | Developer |  | Sales soft delete and restore with status and stamp; Sale and Sale Detail rights enforced | 8 | Not started
S4-DEV-08 | 4 | 8 | Developer |  | Audit log viewer for superadmin | 9 | Not started
S4-DBA-01 | 4 | 7 | DB Admin |  | Query: sales totals and line amounts | 2 | Not started
S4-DBA-02 | 4 | 7 | DB Admin |  | Payment balance view | 4 | Not started
S4-DBA-03 | 4 | 7 | DB Admin |  | Report queries: master list, active/all employees, employee job history, Top Customers/Products/Sales (date range, Top N) | 5 | Not started
S4-DBA-04 | 4 | 8 | DB Admin |  | Audit log query with filters | 6 | Not started
S4-DBA-05 | 4 | 8 | DB Admin |  | Verify delete rules for sales with details or payments | 7 | Not started
S4-DBA-06 | 4 | 8 | DB Admin |  | Final DB review: rebuild from migrations, backup, docs | 9 | Not started
S4-TST-01 | 4 | 7 | Tester |  | Test cases: sales transaction and price-as-of-date | 5 | Not started
S4-TST-02 | 4 | 8 | Tester |  | Payment and balance tests | 7 | Not started
S4-TST-03 | 4 | 8 | Tester |  | Report tests: all seven reports (date range, Top N, per-report rights, Print / Save as PDF) | 8 | Not started
S4-TST-04 | 4 | 8 | Tester |  | End-to-end test: register, approve, assign rights, login, sell, pay, run reports | 8 | Not started
S4-TST-05 | 4 | 8 | Tester |  | Full regression across all modules | 9 | Not started
S4-TST-06 | 4 | 8 | Tester |  | Final test sign-off report | 9 | Not started
S4-UIX-01 | 4 | 7 | UI/UX Designer |  | Wireframes: sales entry and line items | 2 | Not started
S4-UIX-02 | 4 | 7 | UI/UX Designer |  | Wireframes: payment and balance screens | 3 | Not started
S4-UIX-03 | 4 | 7 | UI/UX Designer |  | Report screens (7 reports, filters, Print / Save as PDF) and audit-viewer design | 4 | Not started
S4-UIX-04 | 4 | 7 | UI/UX Designer |  | Hi-fi mockups and handoff notes | 5 | Not started
S4-UIX-05 | 4 | 8 | UI/UX Designer |  | Final UI consistency and usability pass | 9 | Not started
S4-SM-01 | 4 | 7 | Scrum Master |  | Sprint 4 planning notes and board | 1 | Not started
S4-SM-02 | 4 | 7 | Scrum Master |  | Mid-sprint check and impediment log | 5 | Not started
S4-SM-03 | 4 | 8 | Scrum Master |  | Release checklist and demo script | 8 | Not started
S4-SM-04 | 4 | 8 | Scrum Master |  | Collect final peer evaluations | 9 | Not started
S4-SM-05 | 4 | 8 | Scrum Master |  | Final review, retrospective and project report | 10 | Not started

## Summary
Progress Summary (planned vs merged PRs)
Formulas read the Task Plan sheet. 'Merged' = done.
Role | S1 planned | S1 merged | S2 planned | S2 merged | S3 planned | S3 merged | S4 planned | S4 merged | Total planned | Total merged | % done
Developer | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 32 | 0 | 0%
DB Admin | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 24 | 0 | 0%
Tester | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 24 | 0 | 0%
UI/UX Designer | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 20 | 0 | 0%
Scrum Master | 5 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 20 | 0 | 0%
Team total | 30 | 0 | 30 | 0 | 30 | 0 | 30 | 0 | 120 | 0 | 0%
Note: planned task counts per sprint (8/6/6/5/5) equal each role's full-score PR target (midterm target; final target = 3 sprints x same count).

## Change Log
Change Log: User Management and Reports added within the same 8 weeks
Fixed limits kept: 4 sprints x 2 weeks = 8 weeks, and the per-role PR targets (8/6/6/5/5 per sprint). New work was fitted in by merging small tasks, not by adding tasks or weeks. Light-blue cells on Task Plan = revised rows.
Check: total tasks | 120 | Last week used | 8 | Revised tasks | 32
Task ID | Role | Sprint | Before | After | Old due day | New due day | Why
S1-DEV-03 | Developer | 1 | Login and logout with session handling | Login and logout with session handling; password hashing and set-password on first login; blocked users cannot sign in | 5 | 6 | Merged old DEV-03 + DEV-04 (login + hashing/set-password) to free one PR slot; blocked-user check added (guide 3.8).
S1-DEV-04 | Developer | 1 | Password hashing and set-password on first login | Reset password: request, emailed token, reset form | 6 | 7 | Former DEV-05 moved up one ID after the merge above; text unchanged.
S1-DEV-05 | Developer | 1 | Reset password: request, emailed token, reset form | User Management screen: user list, Add User, Edit User, Block/Unblock; Admin manages Users only and Superadmin accounts are hidden | 7 | 8 | NEW: the User Management module in the guide (3.8) had no PR. Uses the slot freed by the merge.
S1-DEV-07 | Developer | 1 | Admin/superadmin: assign per-module rights (view, edit, delete); log every rights change in audit_log | Rights dialog: admin/superadmin assign per-action rights by module (Customer, Product, Human Resources, Sales, Reports) with module checkbox and All/None; log every rights change in audit_log | 9 | 9 | Guide uses per-action rights (36), not only view/edit/delete per module.
S1-DEV-08 | Developer | 1 | Main page: module tiles by view right, plus server-side permission check | Main page: sidebar and module tiles by role and rights, plus server-side permission check | 9 | 9 | Menu now follows per-action rights and role, as in the guide dashboards.
S1-DBA-03 | DB Admin | 1 | Migration: app_user, role, module, user_permission (with soft delete) | Migration: app_user (role, blocked flag), role, module, rights catalogue, user_permission (with soft delete) | 4 | 4 | Needs a blocked flag and a per-action rights catalogue to support User Management.
S1-DBA-05 | DB Admin | 1 | Seed data: one superadmin account per team member, 4 modules, default roles (no passwords in the repo; first password set via one-time set-password link) | Seed data: one superadmin account per team member, modules (Customer, Product, Human Resources, Sales, Reports), the per-action rights catalogue (36 rights, guide 3.8), default roles (no passwords in the repo; first password set via one-time set-password link) | 5 | 5 | Seed matches the guide: five rights modules plus the 36-right catalogue (old text said 4 modules).
S1-TST-02 | Tester | 1 | Test cases: register and login | Test cases: register, login and logout, set and reset password (expired and reused token) | 5 | 7 | Merged old TST-02 + TST-03 to free one test slot.
S1-TST-03 | Tester | 1 | Test cases: set and reset password (expired and reused token) | Test cases: User Management (add, edit, block/unblock, approve, designate admin; Admin cannot see or edit Superadmin; last-superadmin guard) | 7 | 8 | NEW: tests for the User Management screen.
S1-TST-04 | Tester | 1 | Permission matrix tests (superadmin/admin/user x view/edit/delete), using registered and approved test accounts for admin and user | Permission matrix tests (superadmin/admin/user x each right), using registered and approved test accounts; menu, buttons and server all follow the rights | 9 | 9 | Per-action rights; checks the UI and the server agree (a hidden button is not enough).
S1-UIX-03 | UI/UX Designer | 1 | Wireframes: main page and user-rights management | Wireframes: main page, User Management list and Rights dialog | 4 | 4 | Adds the User Management list screen to the wireframes.
S1-UIX-04 | UI/UX Designer | 1 | Hi-fi mockups and developer handoff notes | Hi-fi mockups (login, register, main page, User Management, Rights dialog) and developer handoff notes | 6 | 6 | Mockups now cover User Management.
S1-SM-02 | Scrum Master | 1 | Sprint 1 board: stories with acceptance criteria | Sprint 1 board: stories with acceptance criteria; map all six guide modules to sprints within the 8-week limit | 1 | 1 | Scrum Master keeps the module-to-sprint map so nothing slips past week 8.
S2-DEV-07 | Developer | 2 | Price history: add price with effective date | Price history: add, edit and delete price with effective date | 8 | 8 | Guide price dialog has Edit and Delete as well as Add.
S2-DEV-08 | Developer | 2 | Current-price display on product page; permission checks across both modules | Current-price display on product page; per-action rights checks (Add/Edit/Delete) across both modules | 9 | 9 | Aligned with per-action rights.
S2-TST-04 | Tester | 2 | Permission tests per module | Per-right permission tests for customer and product (Add/Edit/Delete, price rights) | 8 | 8 | Aligned with per-action rights.
S3-DEV-06 | Developer | 3 | Job history: add promotion or transfer (effective date, salary) | Job history: add, edit and delete promotion or transfer (effective date, salary) | 7 | 7 | Guide has Add/Edit/Delete Job History rights.
S3-DEV-08 | Developer | 3 | Restrict salary visibility by permission | Restrict job history and salary visibility with the View Job History right | 9 | 9 | Aligned with the guide rights list.
S3-TST-04 | Tester | 3 | Salary visibility and permission tests | Salary visibility and HR per-right permission tests | 8 | 8 | Aligned with per-action rights.
S4-DEV-01 | Developer | 4 | Sales list with search | Sales list with search and New Sale header (auto-numbered transaction, customer and salesperson drop-downs) | 2 | 3 | Merged old DEV-01 + DEV-02 (list + create) to free a slot for Reports.
S4-DEV-02 | Developer | 4 | Create sales transaction (customer, salesperson, date) | Sale details: add, edit and delete line items (product, quantity); auto-fill unit price from price history as of sales date | 3 | 5 | Merged old DEV-03 + DEV-04 (line items + price lookup).
S4-DEV-03 | Developer | 4 | Add line items (product, quantity) | Record payment against a transaction | 4 | 6 | Former DEV-05; renumbered after the merges.
S4-DEV-04 | Developer | 4 | Auto-fill unit price from price history as of sales date | Reports module, part 1: Product Master List, Active Employees, All Employees, Employee Job History (per-report rights, Print / Save as PDF) | 5 | 6 | NEW: Reports module from the guide (3.7) had only one summary report.
S4-DEV-05 | Developer | 4 | Record payment against a transaction | Reports module, part 2: Top Customers, Top Products, Top Sales (date range, Top N, per-report rights, Print / Save as PDF) | 6 | 7 | NEW: replaces the single Sales summary report with the three sales reports in the guide.
S4-DEV-06 | Developer | 4 | Balance view per transaction and customer | Balance view per transaction and customer | 7 | 7 | Former DEV-06; renumbered.
S4-DEV-07 | Developer | 4 | Sales summary report | Sales soft delete and restore with status and stamp; Sale and Sale Detail rights enforced | 8 | 8 | NEW: the guide shows deleted sales (T-004) and Restore; old plan had no dev PR for it.
S4-DBA-03 | DB Admin | 4 | Report queries | Report queries: master list, active/all employees, employee job history, Top Customers/Products/Sales (date range, Top N) | 5 | 5 | Covers all seven guide reports.
S4-UIX-03 | UI/UX Designer | 4 | Report and audit-viewer design | Report screens (7 reports, filters, Print / Save as PDF) and audit-viewer design | 4 | 4 | Covers the Reports module screens.
S4-TST-01 | Tester | 4 | Test cases: sales transaction | Test cases: sales transaction and price-as-of-date | 3 | 5 | Merged old TST-01 + TST-02.
S4-TST-02 | Tester | 4 | Price-as-of-date tests | Payment and balance tests | 5 | 7 | Former TST-03; renumbered.
S4-TST-03 | Tester | 4 | Payment and balance tests | Report tests: all seven reports (date range, Top N, per-report rights, Print / Save as PDF) | 7 | 8 | NEW: tests for the Reports module.
S4-TST-04 | Tester | 4 | End-to-end test: register, approve, login, sell, pay | End-to-end test: register, approve, assign rights, login, sell, pay, run reports | 8 | 8 | Now includes User Management and Reports in the chain.